## Sites
SiteID | SiteName
1 | Lancing College
2 | Lancing Prep Worthing
3 | Lancing Prep Hove
4 | Little Lancing Nursery & Forest School

## Projects
ID | Name | AssetType | AssetName | Site | BuildingOrArea | Status | StartDate | EndDate | Owner | LeadUser | CurrentSpend | ProjectedSpend | Budget | BaselineEstimate | RiskRating | RiskSummary
1 | Chapel West Porch Stonework | Religious / Historic | Chapel – West Porch | Lancing College | Chapel / Lower Quad | Planned | 2026-05-01 | 2026-10-31 | Estates | Estates Bursar | 0 | 250000 | 230000 | 220000 | Medium | Weather and stone supply lead times for listed chapel.
2 | Boarding House 5 – Roof & Gutter Refurbishment | Residential / Boarding | Boarding House 5 – Dorm Roof | Lancing College | Boarding Houses Zone | In Progress | 2025-09-15 | 2025-12-01 | Estates | Estates Manager | 40000 | 38000 | 45000 | 48000 | Low | Works scheduled out of term-time to avoid pupil disruption.
3 | Sports Hall – HVAC & Roof Works | Sports / Indoor | Sports Hall | Lancing College | Indoor Sports Complex | Planned | 2026-04-01 | 2026-07-15 | Estates & Maintenance | Director of Sport | 0 | 55000 | 60000 | 58000 | High | Programme risk with exams and sports fixtures; noisy works.
4 | Astro Pitch 2 Floodlight Upgrade | Sports / Outdoor Pitch | Astro Pitch 2 | Lancing College | Sports Fields | Planned | 2026-08-01 | 2026-09-15 | Grounds & Maintenance | Grounds Manager | 0 | 18000 | 20000 | 18000 | Medium | Planning / neighbour consultation for light-spill.
5 | Dining Hall Kitchen Refresh – Phase 2 | Catering / Dining | Main Dining Hall Kitchen | Lancing College | Central Dining Block | Completed | 2025-04-01 | 2025-06-01 | Catering & Estates | Head of Catering | 52000 | 52000 | 52000 | 50000 | Low | New equipment commissioning only.
6 | Dorm Block 3 – Fire Alarm & Emergency Lighting Upgrade | Life Safety / M&E | Dorm Block 3 | Lancing College | Boarding Houses Zone | In Progress | 2025-10-10 | 2025-11-30 | Estates & Safety | Health & Safety Officer | 8000 | 14000 | 15000 | 14000 | High | Regulatory deadline and term-time access limitations.
7 | Prep Worthing – Classroom 4 & 5 Refurbishment | Teaching / Classroom | Classrooms 4–5 | Lancing Prep Worthing | Main Teaching Block – First Floor | Planned | 2025-07-20 | 2025-08-28 | Prep Worthing Estates | Head of Prep Worthing | 0 | 28000 | 30000 | 28000 | Medium | Tight summer window for AV and furniture install.
8 | Prep Worthing – Playground Resurfacing & Drainage | Grounds / Play Area | Front Playground | Lancing Prep Worthing | Outdoor Play Zone | Planned | 2026-04-05 | 2026-04-20 | Prep Worthing Estates | Deputy Head | 0 | 15000 | 16000 | 15000 | Low | Weather dependency only; works in Easter break.
9 | Prep Hove – Hall Lighting & AV Upgrade | Hall / Assembly | School Hall | Lancing Prep Hove | Central Hall | Planned | 2025-10-20 | 2025-11-10 | Prep Hove Estates | Head of Prep Hove | 0 | 12000 | 13000 | 12000 | Medium | Coordination with school productions and events.
10 | Prep Hove – Roof Repairs over Early Years Classrooms | Roof / Envelope | EYFS Roof Zone | Lancing Prep Hove | Early Years Block | In Progress | 2025-08-05 | 2025-09-01 | Prep Hove Estates | Site Manager – Hove | 6000 | 10000 | 12000 | 11000 | Low | Scaffold interface with neighbouring properties.
11 | Little Lancing – Forest School Path & Fencing Improvements | Grounds / Forest School | Forest School Area | Little Lancing Nursery & Forest School | Woodland Learning Area | Planned | 2025-08-10 | 2025-08-24 | Nursery & Estates | Nursery Manager | 0 | 9000 | 10000 | 9000 | Medium | Ground conditions and safeguarding fencing requirements.
12 | Little Lancing – Nursery Classroom Refresh | Early Years / Classroom | Nursery Rooms A–C | Little Lancing Nursery & Forest School | Nursery Building | Completed | 2025-03-01 | 2025-04-10 | Nursery & Estates | Nursery Manager | 18000 | 18000 | 19000 | 18000 | Low | Minor snagging only post‑completion.

## Tasks
ProjectID | Phase | Title | Assignee | DueDate | Status
1 | Pre | Confirm heritage scope with architect | Estates Manager | 2026-02-15 | Not Started
1 | Pre | Update asbestos and lead register | H&S Officer | 2026-03-01 | Not Started
1 | During | Scaffold erection and access checks | Main Contractor | 2026-05-10 | Not Started
1 | Post | Snagging and diocesan sign‑off | Estates Manager | 2026-10-25 | Not Started
2 | Pre | Issue works notice to House staff & parents | Boarding House Warden | 2025-07-01 | In Progress
2 | During | Strip tiles and renew gutters | Roofing Contractor | 2025-10-15 | Not Started
2 | Post | Roof inspection and sign‑off | Estates Manager | 2025-12-05 | Not Started
3 | Pre | HVAC design and specification sign‑off | Director of Sport | 2026-02-01 | Not Started
3 | During | Install new AHUs and ducting | M&E Contractor | 2026-05-20 | Not Started
3 | Post | Test commissioning & BMS integration | M&E Contractor | 2026-07-10 | Not Started
7 | Pre | Agree classroom layouts with staff | Head of Prep Worthing | 2025-06-10 | Not Started
7 | During | Install new flooring and LED lighting | Main Contractor | 2025-08-05 | Not Started
7 | Post | IT and AV testing | IT Support | 2025-08-25 | Not Started
11 | Pre | Check tree survey & safeguarding requirements | Nursery Manager | 2025-07-15 | Not Started
11 | During | Install new paths and fencing | Groundworks Contractor | 2025-08-18 | Not Started
11 | Post | Forest School safety walk‑through | H&S Officer | 2025-08-24 | Not Started

## Contractors
ContractorID | Name | Company | Trade | Phone | Email | Accreditations | DBS Checked | Preferred | Notes
1 | Main Building Contractor | South Downs Builders Ltd | General Building / Historic Refurb | +44 1273 111111 | projects@southdownsbuilders.example | CHAS, Constructionline | Yes | Good for chapel and boarding house works; familiar with heritage constraints. | Preferred for classroom and housing refurbishments.
2 | M&E Services Contractor | BrightSpark Electrics & Plumbing | Electrical / Mechanical | +44 1273 222333 | office@brightsparkmep.example | NICEIC | Yes | Use for lighting upgrades, HVAC, fire alarm and emergency lighting. | Use for LED upgrades and power work in teaching spaces.
3 | Sports Surfaces Contractor | Elite Sports Surfaces Ltd | Pitch Surfacing & Floodlighting | +44 1273 333444 | ops@elitesports.example | UK Surfacing Assoc. | Yes | Handles astro pitches, line marking and floodlight installations. | Handles roadway resurfacing and line markings.
4 | Kitchen & Catering Refurb | CampusCatering Fitters Ltd | Catering / Kitchen Installations | +44 1273 444555 | projects@campuscatering.example | HACCP Compliant Installers | Yes | Dining hall and servery refurbishments across sites. | Specialists in gates, barriers and access control integration.
5 | Pool & Aquatics Contractor | HydroBuild Pools Ltd | Pool Refurbishment / M&E | +44 1273 555666 | support@hydrobuild.example | PoolSafe, CHAS | Yes | For pool plant, re‑tiling, and water treatment improvements. | Call for CCTV surveys and reactive drainage issues.
6 | Groundworks & Civils | Downs Groundworks & Civil Ltd | Civils / Drainage / Roadworks | +44 1273 666777 | info@downscivils.example | NHSS Sector 16 | Yes | Use for roadway resurfacing, playground works, drainage, and forest paths.

## HealthAndSafety
HSID | ProjectID | WarningType | Description | Severity | Location | ControlMeasures | Notes
1 | 1 | Heritage / Asbestos Risk | Chapel roof voids may contain legacy asbestos and lead-based materials. | High | Lancing College – Chapel roof and west porch | Full asbestos survey; licensed removal where required; exclusion zones; PPE. | Coordinate with heritage architect and diocesan authorities.
2 | 3 | Working at Height | Sports Hall roof access and plant platform works at height. | Medium | Lancing College – Sports Hall roof | Use tower scaffold; edge protection; harnesses; trained operatives only. | Schedule noisy works out of exam periods.
3 | 6 | Fire Systems / Life Safety | Dorm Block 3 fire alarm and emergency lighting upgrades during term time. | High | Lancing College – Dorm Block 3 | Phased shutdown; temporary alarms; hot works permits; evening briefings with House staff. | Notify local fire authority prior to system downtime.
4 | 7 | Dust / Noise in Teaching Areas | Classroom strip‑out and flooring works in teaching block. | Medium | Lancing Prep Worthing – Classrooms 4–5 | Seal off working zone; out-of-hours works where possible; cleaning before term restarts. | Ensure safeguarding arrangements for contractors on site.
5 | 11 | Ground Conditions / Slips & Trips | Uneven woodland surfaces and open excavations during path installation. | Medium | Little Lancing – Forest School Area | Barrier fencing; clear signage; works only when children are off site. | Check impact on tree roots with arboriculturalist.

## ProjectContractors
LinkID | ProjectID | ContractorID | Role | Notes
1 | 1 | 1 | Main Contractor | Lead contractor for chapel stonework and porch refurbishment.
2 | 1 | 2 | M&E Support | Check any cabling / lighting impacted by works.
3 | 2 | 1 | Main Contractor | Roofing and gutter replacement on Boarding House 5.
4 | 3 | 2 | M&E Contractor | HVAC and roof plant replacement in Sports Hall.
5 | 4 | 3 | Sports Lighting Contractor | Supply and install new LED floodlights.
6 | 5 | 4 | Kitchen Fit-out | Install new servery counters and catering equipment.
7 | 6 | 2 | Fire & Emergency Systems Contractor | Upgrade alarm panels and emergency lighting.
8 | 7 | 1 | Main Contractor | Classroom finishes and partitions.
9 | 8 | 6 | Groundworks Contractor | Playground surface and drainage improvements.
10 | 11 | 6 | Groundworks Contractor | Forest School paths and fencing.
11 | 12 | 1 | Main Contractor | Interior refresh and decorations.